## Sheet1
PROJECT NUMBER | SSAD03
PROJECT NAME | Artificial Intelligence Bot for FAQ
PROJECT MENTOR (sponsor) | Jayanth Rasamsetti
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (August 8- August 14)
Fix meeting with client | Coordination | Vighnesh Chenthil Kumar | 0.5 | 0.25 | Done |  | 0.25 | 50
GIT Repository setup | Preparation | Done by TA’s | 1 | 1.5 | Done |  | -0.5 | -50
Structure Git repository with lints and setup Node environment | Preparation | Anubhab Sen | 1 | 0.5 | Done |  | 0.5 | 50
Client meeting | Coordination | Vighnesh Chenthil Kumar | 1 | 0.5 | Done |  | 0.5 | 50
Research existing technology | Preparation | Anubhab Sen, Vighnesh Chenthil Kumar | 2 | 0.5 | Done |  | 1.5 | 75
Project Concept Writeup | Documentation | Vighnesh Chenthil Kumar | 2 | 1 | Done |  | 1 | 50
Identify role owners | Preparation | Jayanth | 1 | 0.25 | Done |  | 0.75 | 75
Team Meeting | Coordination | Vighnesh Chenthil Kumar | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 1 | 1.5 | Planned |  | -0.5 | -50
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar, Ananya Trivedi | 1 | 0.5 | Done |  | 0.5 | 50
Week 2 (August 15 - August 21)
Status tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 1 |  | Ongoing |  | 1 | 100
Client meeting | Coordination | Vighnesh Chenthil Kumar | 0.5 | 0.1 | Done |  | 0.4 | 80
Research front end technologies | Preparation | Anubhab Sen | 1 | 0.5 | Done |  | 0.5 | 50
Build bare bones website to practice new technology | Preparation | Anubhab Sen | 6 |  | Ongoing |  | 6 | 100
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar | 1 | 1 | Done |  | 0 | 0
Week 3 (August 22 – August 28)
Status tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.3 |  | Ongoing |  | 0.3 | 100
Project Plan Writeup | Documentation | Vighnesh Chenthil Kumar | 2 | 2.5 | Done |  | -0.5 | -25
Prepare sample FAQ page to train bot on | Preparation | Anubhab Sen | 1 | 1 | Done |  | 0 | 0
Train bot on sample data | Preparation | Anubhab Sen | 2.5 | 2 | Done |  | 0.5 | 20
Week 4 (August 29 – Sep 5)
Status tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.1 |  | Ongoing |  | 0.1 | 100
Client meeting | Coordination | Vighnesh Chenthil Kumar | 0.1 | 0.1 | Done |  | 0 | 0
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar | 1 | 0.5 | Done |  | 0.5 | 50
Week 5(Sep 6- Sep 12)
Status tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.1 |  | Ongoing |  | 0.1 | 100
Software Requirements Specification Writeup | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 2 | 2 | Done |  | 0 | 0
Integrating to bot front end | Preparation | Anubhab Sen | 10 |  | Ongoing |  | 10 | 100
Week 6