## Sheet1
PROJECT NUMBER | SSAD03
PROJECT NAME | Artificial Intelligence Bot for FAQ
PROJECT MENTOR (sponsor) | Jayanth Rasamsetti
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (August 8- August 14)
Fix meeting with client | Coordination | Vighnesh Chenthil Kumar | 0.5 | 0.25 | Done |  | 0.25 | 50
GIT Repository setup | Preparation | Done by TA’s | 1 | 1.5 | Done |  | -0.5 | -50
Structure Git repository with lints and setup Node environment | Preparation | Anubhab Sen | 1 | 0.5 | Done |  | 0.5 | 50
Client meeting | Coordination | Vighnesh Chenthil Kumar | 1 | 0.5 | Done |  | 0.5 | 50
Research existing technology | Preparation | Anubhab Sen, Vighnesh Chenthil Kumar | 2 | 0.5 | Done |  | 1.5 | 75
Project Concept Writeup | Documentation | Vighnesh Chenthil Kumar | 2 | 1 | Done |  | 1 | 50
Identify role owners | Preparation | Jayanth | 1 | 0.25 | Done |  | 0.75 | 75
Team Meeting | Coordination | Vighnesh Chenthil Kumar | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 1 | 1.5 | Done |  | -0.5 | -50
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar, Ananya Trivedi | 1 | 0.5 | Done |  | 0.5 | 50
Week 2 (August 15 - August 21)
Status Tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 1 | 0.5 | Done |  | 0.5 | 50
Client meeting | Coordination | Vighnesh Chenthil Kumar | 0.5 | 0.1 | Done |  | 0.4 | 80
Research front end technologies | Preparation | Anubhab Sen | 1 | 0.5 | Done |  | 0.5 | 50
Build bare bones website to practice new technology | Preparation | Anubhab Sen | 6 | 5.5 | Done |  | 0.5 | 8.3333
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar | 1 | 1 | Done |  | 0 | 0
Week 3 (August 22 – August 28)
Status Tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.3 | 0.25 | Done |  | 0.05 | 16.6667
Project Plan Writeup | Documentation | Vighnesh Chenthil Kumar | 2 | 2.5 | Done |  | -0.5 | -25
Prepare sample FAQ page to train bot on | Preparation | Anubhab Sen | 1 | 1 | Done |  | 0 | 0
Train bot on sample data | Preparation | Anubhab Sen | 2.5 | 2 | Done |  | 0.5 | 20
Week 4 (August 29 – Sep 5)
Status Tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.1 | 0.16 | Done |  | -0.06 | -60
Client meeting | Coordination | Vighnesh Chenthil Kumar | 0.1 | 0.1 | Done |  | 0 | 0
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar | 1 | 0.5 | Done |  | 0.5 | 50
Market Research on Food Delivery sector | Preparation | Vighnesh Chenthil Kumar | 1.5 | 1 | Done |  | 0.5 | 33.3333
Market Research on Travel sector | Preparation | Anubhab Sen | 1 | 0.5 | Done |  | 0.5 | 50
Week 5 (Sep 6 - Sep 12)
Status Tracker | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.1 | 0.1 | Done |  | 0 | 0
Software Requirements Specification Writeup | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 2 | 2 | Done |  | 0 | 0
Integrating to bot front end | Preparation | Anubhab Sen | 10 | 9.5 | Done |  | 0.5 | 5
Week 6 (Sep 13 - Sep 19)
Status Tracker | Documentation | Vighnesh Chenthil Kumar | 0.1 | 0.1 | Done |  | 0 | 0
Research NLP technology to better the bot | Preparation | Vighnesh Chenthil Kumar | 2 | 1.5 | Done |  | 0.5 | 25
Week 7 (Sep 20 - Sep 26)
Status Tracker | Documentation | Vighnesh Chenthil Kumar | 0.1 | 0.25 | Done |  | -0.15 | -150
Client meeting | Coordination | Vighnesh Chenthil Kumar | 0.5 | 0.1 | Done |  | 0.4 | 80
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar | 0.75 | 0.5 | Done |  | 0.25 | 33.3333
Finalise a food delivery startup | Preparation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.1 | 0.5 | Done |  | -0.4 | -400
Go through Pandora Bots Tutorial | Preparation | Anubhab Sen, Vighnesh Chenthil Kumar, Ananya Trivedi | 3 | 4 | Done |  | -1 | -33.3333
Train the bot on all possible FAQs | Preparation | Anubhab Sen, Vighnesh Chenthil Kumar, Ananya Trivedi | 15 |  | Ongoing |  | 15 | 100
Week 8 (Sep 27 - October 3)
Status Tracker | Documentation | Vighnesh Chenthil Kumar | 0.1 | 0.1 | Done |  | 0 | 0
Client meeting | Coordination | Vighnesh Chenthil Kumar | 0.5 | 0.4 | Done |  | 0.1 | 20
Minutes of Meeting Writeup | Documentation | Vighnesh Chenthil Kumar | 0.75 | 0.5 | Done |  | 0.25 | 33.3333
Test Plan Writeup | Documentation | Anubhab Sen | 0.75 | 0.5 | Done |  | 0.25 | 33.3333
Design Document Writeup | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 0.5 | 0.8 | Done |  | -0.3 | -60
Slides for R1 Presentation | Documentation | Anubhab Sen, Vighnesh Chenthil Kumar | 2 | 2.5 | Done |  | -0.5 | -25
Week 9 (October 4 - October 10)