## Sheet1
Test Planner and Tracker |  |  | SSAD 03 | Anubhab Sen, Vighnesh Chenthil Kumar, Ananya Trivedi
Test No. ID | Related Use case | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | Comments (if test case failed) | R2 Outcome (color code cell background) | Comments (if test case failed)
1 | Differently asked same question |  | Write the question in 7 different ways and feed to bot | Same answer given | Same answer given
2 | User questions passed to the UI |  | Type something in UI and hit return | Query rendered in chat box | Query rendered in chat box | Initial error fixed
3 | Bot responds to the questions |  | User input given | Bot responds as trained | Bot responds as trained | Curl error fixed
4 | Compilation of AIML |  | User input given | Bot responds ie no compilation error | Bot responds ie no compilation error | API key and bot name error fixed
5 | Bot responds slightly different to similar questions |  | User asks same question in different ways | Bot responds slightly differently | Bot responds in same manner | To be fixed before R2 with a randomize mechanism
6 | Casual Questions |  | User asks questions unrelated to the site | Bot responds as required | not implemented
7 | Big Red Button |  | Button to transfer to live chat with exec | Link to messenger chat | not implemented
8 | Questions asked records |  | Record questions asked in a log | File with questions asked | not implemented
9 | Embed bot on site |  | Embed the bot on Heroku and see how it performs | No problem embedding and everything working as expected | Bot works exactly as when it is done locally
10 | Extract information from user |  | Detect when user inputs an email id and store it | emails input if valid are stored | not implemented
11 | Recommendations |  | Provide list of most asked questions to user | Provides some popular questions set by the business | not implemented
12 | Embed bot with all other features complete |  | Final test deployment of bot | Every feature works | can’t be performed yet
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30